## Sheet1
Tasks | Work estimate in Hr | Detail
Learning MODAPTS/Analysing code & requirements | 80
Client management | 40
MODAPTS Analysis Sheet for Performance Standards | 160 | Element Classes: Movements, Terminal, and Auxiliary. Low vs. High Conscious Control. Simultaneous Moves.
MODAPTS Reports | 160 | OIS Sheets. Advanced Report. Ergonomics. Comparitive reports. Plant Strucutre. Plant Reporting.
Implement recurring subscription billing payments | 160 | Plans management. Collect billing information. Create subscription and handling its events: subscription trial will end, Invoice payment succeeded, Invoice payment failed... Other subscription scenarios: change plan, cancel subscription.
Plant structure management | 40 | Creation of the plant structure and organize studies based on it.
Setup production environment | 40
Meetings | 40 | Already consumed 8 hours.
Total Hr | 720
Cost per Hr in $ | 70
Total Cost in $ | 50400